## Slide 1: Paratext 9 Project Plan
Notes: So there is a Paratext 7.5 server and a Paratext 8.0 server
Kent & Doug Higby probably get a request from Cameroon every so often when I am in search of a Paratext license for someone

## Slide 3: Learning Outcomes
Create a project plan from a base plan
Modify a project plan
Configure task settings
Assign automatic checks to stages
Assign tasks and checks to team members.
Mark individual tasks as completed.
Generate progress charts

## Slide 4: Project Plan - Overview
Prerequisites
Setting up a plan (administrator)
Using a plan (administrator)
Using a plan (translator)
View progress

## Slide 5: Project Plan Prerequistes
Notes: So there is a Paratext 7.5 server and a Paratext 8.0 server
Kent & Doug Higby probably get a request from Cameroon every so often when I am in search of a Paratext license for someone

## Slide 6: First things to consider
Must select the base plan to start from
Must agree on the plan to use
Must have review basic inventory setup
Remove all book permissions from User Permission dialog box.
Set start date and expected completion date in registry
Does the plan need to be localized?

## Slide 7: Basic inventories
Review character inventory
Review punctuation inventory
Review scripture reference settings
Review language settings
Review quotation rules
Review number settings

## Slide 8: Basic inventories
Demo character inventory
Demo punctuation inventory
Demo scripture reference settings

## Slide 9: Project Plan Setting up a plan
Notes: So there is a Paratext 7.5 server and a Paratext 8.0 server
Kent & Doug Higby probably get a request from Cameroon every so often when I am in search of a Paratext license for someone

## Slide 10: Setting up the project plan
Setting project scope
Creating a project plan
Modifying a project plan
Configuring task settings
Assigning checks to stages
Marking Progress to date

## Slide 11: Setting project scope
Notes: Project progress is calculated based on the total number of verses in the books that are included in the project scope. Therefore, the project scope cannot include books without verses (for example, a glossary) even though you intend to include that book in your project.

## Slide 12: Creating a project plan
Selecting a base plan and applying it to project
In the Project Settings menu, click Project Plan
Click Manage Plans
Select a base plan
Click Copy Plan
Click OK

## Slide 13: Creating a project plan
Demo creating a project
Notes: If you add, reorder, or remove stages or tasks, a hyphen followed by the short name of your project is added at the end of the Project Plan name.

## Slide 14: Modifying a project plan
Reorder tasks
Add tasks
Delete tasks
Combine tasks
Notes: If you modify a project plan, a hyphen followed by the short name of your project is added at the end of the Project Plan name.

## Slide 15: Modifying a project plan
Reorder tasks
Tasks can be moved earlier or later in a stage
Tasks can be moved to different stage
Tasks should be placed where they must be completed
Add tasks
Delete tasks
Combine tasks

## Slide 16: Modifying a project plan
Reorder tasks
Add tasks
Select preceding task
Click Add task button
Give the task a name and description
Delete tasks
Combine tasks

## Slide 17: Modifying a project plan
Reorder tasks
Add tasks
Delete tasks
Select task and click on Delete icon or Remove task button
No undo function
Can cancel if you delete the wrong task
Combine tasks

## Slide 18: Modifying a project plan
Reorder tasks
Add tasks
Delete tasks
Combine tasks
Select the task you wish to edit
Edit the name and description
Delete the other task

## Slide 19: Modifying a project plan
Demo reordering a task
Demo adding a task
Demo deleting a task

## Slide 20: Configuring task settings
Three task settings
Mark task as complete
When can this task start
Requires Editing

## Slide 21: Configuring task settings
Three task settings
Mark task as complete
  By chapter of a book
  By entire book
  By entire project
When can this task start
Requires Editing

## Slide 22: Configuring task settings
Three task settings
Mark task as complete
When can this task start
  Dependent tasks: After previous task is complete {for book}
  Dependent tasks: After previous stage is complete {for book}
  Independent tasks: Any time
  Effects the task shown on the translator’s to do list
Requires Editing

## Slide 23: Configuring task settings
Three task settings
Mark task as complete
When can this task start
Requires Editing
  Project name
  No

## Slide 24: Configuring effort settings
Estimate how many verses the team can complete each day for this task.
Easiest books
Easy books
Moderate books
Difficult books

## Slide 25: Configuring task settings
Demo configuring task settings

## Slide 26: Assigning checks to stages
Automatic checks are set at the stage level
In Checks tab in the Project Plan dialog box
At least 20 checks available to you
There are five categories of checks: Basic, Spelling, Unresolved Notes, Back Translation and Other
Each Note tag will have a potential check

## Slide 27: Assigning checks to stages

## Slide 28: Assigning checks to stages
Demo

## Slide 29: Marking progress to date
In the Assignment and Progress dialog box, select Stages Table
Check off stages completed
But automatic checks won’t let you proceed

## Slide 30: Marking progress to date
The Solution
First take a screenshot of your check
Temporarily turn off automated checks
Use the Stages Table to mark the completed stages for existing books
Turn the automated checks back on.

## Slide 31: Marking progress to date

## Slide 32: Marking progress to date

## Slide 33: Marking progress to date

## Slide 34: Marking progress to date

## Slide 35: Your Turn
Apply SIL Compact Base plan to your project and save it.
Move tasks to a new location in same stage
Move tasks to new location in different stage
Add new tasks
Delete a task
Combine two tasks into one task
Update description for task
Change task features

## Slide 36: Your Turn
Change stage for a basic check
Change stage for other checks.
Assign tasks for two books to the team.
Assign task to yourself and another task to your partner for the first draft.
Mark tasks as completed.

## Slide 37: Using the Project Plan
What do we do next?
Are we there yet?
Notes: So there is a Paratext 7.5 server and a Paratext 8.0 server
Kent & Doug Higby probably get a request from Cameroon every so often when I am in search of a Paratext license for someone

## Slide 38: Assigning tasks to the team
For administrator to do, first choose a book
In the Assignment and Progress dialog box, there are three columns:
Task/Check
Assigned to
Status

## Slide 39: Assigning tasks to the team
In the Assigned to column, there are options to select:
Unassigned
One team member
(Team)
Assign whole book or range of chapters

## Slide 40: Assigning tasks to the team

## Slide 41: Assigning tasks to the team
There are three kinds of activity for the translators to do
Editing the text
Resolving issues
Marking progress

## Slide 42: Getting Info on Task
Assignments and Progress dialog box
  Hover over the task you want information on
  The description for the task is displayed

## Slide 43: Marking tasks as completed
Check the Status column
  Set the checkbox to mark book as completed
  Click the number range to mark a range of chapters as completed
  Click plus sign to mark next chapter as completed

## Slide 44: Task Table
To see the completion status for tasks by current book, assigned books or by range of books

## Slide 45: Checking My Tasks
Notes: If there are incomplete tasks or checks that are assigned to you in other books, click a link at the lower edge of the dialog to display incomplete tasks or checks that are assigned to you in another book.

## Slide 46: Checking All Tasks

## Slide 47
Demo

## Slide 48: Project Plan – View Progress
How are we doing?
Notes: So there is a Paratext 7.5 server and a Paratext 8.0 server
Kent & Doug Higby probably get a request from Cameroon every so often when I am in search of a Paratext license for someone

## Slide 49: Charts and reports
Team Progress Report
  By Book
  By and Stage
  Forecase Line Chart

## Slide 50: Charts and reports
Project Health Report

## Slide 51
Demo

## Slide 52: Notes
You need to do a Send/Receive after you have made changes to Assignments and Progress window, so that the other team members get the new editing permissions
The blue icon on the upper right hand corner indicates a project has a plan.
Having too many task set to “start anytime”.
Assigning global checks while others are drafting
Notes: Having too many tasks set to “start anytime.” This setting gives flexibility when needed but also opens up the possibility of merge conflicts since tasks in more than stage and in more than one book can be given editing permissions at the same time.
Other problems related to causing conflicts such as assigning global checks such as Spelling and Biblical terms while others are drafting and revising.

## Slide 53: How to make a base plan
Open the project that has a project plan that you wish to share as a base plan.
In the Project Plan window, shift-click Manage Plans
Make any other changes to the plan
Click Save as a Base Plan.
Give the plan a unique name.

## Slide 54: How to distribute a base plan
Copy the project plan file in the StandardPlans subfolder in the MyParatextProjects folder to the computer that needs it in the StandardPlans subfolder.
The administrator for each project will need to choose the new base plan for their projects
Notes: The base plan is an XMl in the _StandardPlans subfolder under the My Paratext 9 Projects folder,

## Slide 55: Your Turn
Assign tasks for two books to the team.
Assign a task to yourself and another task to your partner for the first draft.
Mark tasks as completed.
Check the difference between My tasks and All tasks.
Review progress reports

## Slide 56: Summary
A project plan is built upon an _______ plan.
To add a task to the plan, you select ______ task, click _______ button and give the task a name and __________.
You can mark a task as complete by chapter, by ______ or by _______.
Automatic checks are set at the _____ level.
You assigned tasks to a translator via the _________ and _______dialog box.
Notes: You should demonstrate these in Paratext

## Slide 57: Summary
A project plan is built upon an _______ plan.
To add a task to the plan, you select ______ task, click _______ button and give the task a name and __________.
You can mark a task as complete by chapter, by ______ or by _______.
Automatic checks are set at the _____ level.
You assigned tasks to a translator via the _________ and _______dialog box.
Answers: organizational, preceding, Add task, description, book, project, stages, assignments and progress.
Notes: You should demonstrate these in Paratext

## Slide 58: Summary
Tasks assigned to you are shown under _______
Mark individual tasks as completed for a variety of types of tasks (by _______, book or ______) from the _____ column.
Postpone checks by clicking to the ______ of the check.
Show the progress charts of your project using Project > _______ ______.
Notes: You should demonstrate these in Paratext

## Slide 59: Summary
Tasks assigned to you are shown under _______
Mark individual tasks as completed for a variety of types of tasks (by _______, book or ______) from the _____ column.
Postpone checks by clicking to the ______ of the check.
Show the progress charts of your project using Project > _______ ______.
Answers: my tasks, project, chapter, status, right, Progress Charts.
Notes: You should demonstrate these in Paratext